2026

sellsell marketplace updates:

Shaz EJ

# Completed (≈ 97–98%)

### Core Marketplace

✅ User registration and login

✅ Buyer and seller accounts

✅ Product listing creation

✅ Product publishing flow

✅ Product management

✅ Product details pages

✅ Chat between buyer and seller

✅ Contact methods (WhatsApp, phone, etc.)

### AI Search Engine

✅ Arabic search

✅ English search

✅ Semantic search

✅ Attribute extraction

✅ Vehicle search

✅ Natural language search

Examples:

- "Toyota Prado"

- "تويوتا برادو"

- "Black Mercedes S400"

all work through the AI search pipeline.

### AI Seller Assistant

✅ AI title generation

✅ AI description generation

✅ AI specification extraction

✅ AI translations

✅ AI-assisted listing enrichment

### AI Moderation System

✅ Moderation queue

✅ Listing moderation workflow

✅ Admin approve/reject

✅ Moderation dashboard

✅ Agent logs

### Vector Search Infrastructure

✅ Qdrant

✅ Embeddings

✅ Async indexing workers

✅ BullMQ queues

✅ Redis

### Demand Capture System

✅ Save unmet demand

✅ Track buyer requests

✅ Match future products

✅ Demand analytics

### Admin Dashboard

✅ User management

✅ Listing moderation

✅ Demand capture analytics

✅ Search analytics

✅ Platform analytics

✅ Admin crashes fixed

### Notifications System

According to the latest Antigravity report:

✅ Notification center

✅ Notification APIs

✅ Unread counts

✅ Contact click notifications

✅ Buyer inquiry notifications

✅ Demand match notifications

✅ Notification badges

✅ Hot Demand widget

### Infrastructure

✅ Docker

✅ PostgreSQL

✅ Redis

✅ Qdrant

✅ RunPod Ollama

✅ Faster Whisper transcription

✅ Health monitoring

✅ Local storage fallback

✅ Production deployment

# Remaining Before Full MVP Launch

## 1. Upload Storage Finalization

Status: ~80%

Need to verify:

- Production uses local storage

- No dependency on S3

- Upload persistence survives container restarts

Estimated:
0.5 day

## 2. Mobile App Completion

Status: ~70%

Remaining:

- Seller dashboard polish

- Notifications integration

- Final UI fixes

- End-to-end testing

Estimated:
5–10 days

## 3. Push Notifications

Status: ~40%

Need:

- Firebase

- Apple APNS

- Mobile notification delivery

Estimated:
2–3 days

## 4. Production QA

Status: ~70%

Need:

- Seller flow testing

- Buyer flow testing

- Search testing

- Arabic testing

- Load testing

Estimated:
3–5 days

## 5. Analytics & Monitoring

Status: ~75%

Need:

- Error dashboard

- AI monitoring

- Queue monitoring

- Business KPIs

Estimated:
2–3 days

# Month 2 Features (Growth Phase)

Not required for launch, but planned:

### Seller Intelligence

🔲 Hot products dashboard

🔲 Market demand trends

🔲 Buyer demand insights

### Buyer Intelligence

🔲 Smart recommendations

🔲 Better ranking

🔲 Better search relevance

### Auto Matching

🔲 New listing → notify interested buyers

🔲 Demand → seller matching

# Month 3 Features (AI Marketplace Vision)

### Buyer Agent

User says:

Find me a Toyota Prado under 100,000 QAR

Agent:

- Searches

- Compares

- Ranks

- Explains

Automatically.

### Seller Agent

Helps sellers:

- Price products

- Improve listings

- Identify demand

### AI Analytics

Management dashboard:

- Most requested products

- Conversion rates

- Buyer trends

- Seller performance

# Current Project Status

| Area | Status |
| --- | --- |
| Marketplace Core | ✅ 100% |
| AI Search | ✅ 95% |
| AI Seller Assistant | ✅ 90% |
| AI Moderation | ✅ 95% |
| Notifications | ✅ 90% |
| Admin Dashboard | ✅ 95% |
| Infrastructure | ✅ 95% |
| Mobile App | 🟡 70% |
| Push Notifications | 🟡 40% |
| Final QA | 🟡 70% |

### Overall Assessment

Core platform: ~98% complete

Launch-ready MVP: ~90–95% complete

AI-powered marketplace vision (agents, advanced automation, growth systems): ~70% complete

If the current pace continues, you can realistically have a solid public MVP ready for Fahad and Sultan within 1–2 weeks, and a much more advanced AI marketplace platform within 2–3 months.